## Blank Weekly Sheet
			Jan	Jan	Jan	Jan	Jan	Jan	Jan	Jan	Jan	Jan	Jan	Feb	Feb	Feb	Feb	Feb	Feb	Feb	Feb	Feb	Feb	Feb	Feb	Feb	Feb	Feb	Feb	Feb	Feb	Feb	Feb	Feb	Feb	Feb	Feb	Feb	Feb	Feb	Feb	Mar	Mar	Mar	Mar	Mar	Mar	Mar	Mar	Mar	Mar	Mar	Mar	Mar	Mar	Mar	Mar	Mar	Mar	Mar	Mar	Mar	Mar	Mar	Mar	Mar	Mar	Mar	Mar	Mar	Mar	Mar	Apr	Apr	Apr	Apr	Apr	Apr	Apr	Apr	Apr	Apr	Apr	Apr	Apr	Apr	Apr	Apr	Apr	Apr	Apr	Apr	Apr	Apr	Apr	Apr	Apr	Apr	Apr	Apr	Apr	Apr	May	May	May	May	May	May	May	May	May	May	May	May	May	May	May	May	May	May	May	May	May	May	May	May	May	May	May	May	May
Mon Jan 21
Project Week		W1	W2	W3	W4	W5	W6	W7	W8	W9	W10	W11	W12	W13	W14	W15	W16	W17	W18	W19	W20	W21	W22	W23	W24
ISO WEEK NUM		W4	W5	W6	W7	W8	W9	W10	W11	W12	W13	W14	W15	W16	W17	W18	W19	W20	W21	W22	W23	W24	W25	W26	W27
MONTH		JAN		FEB				MAR				APR					MAY				JUN				JUL
(MON)DAY		21	28	04	11	18	25	04	11	18	25	01	08	15	22	29	06	13	20	27	03	10	17	24	01
Overview Schedule
Deadlines					Structure Submission				Pre-Study Submission									Report Submission	Examiner Submission	Ann B. Submission		Presentation Submission
Project Structure (3-4 Weeks)
Draft #1
Draft #2
Draft #3
Pre-Study
Data-set Evaluation
Theory search
Related Work Search
Summary & Refining Resources
Introduction Draft
Part 3 (8-10 Weeks)
Methodology
Finding & Deciding on tools
Writing Background
Writing Method

Implementation
Pre-Processing, Feature Selection
Multiple Clustering Implementations
Sampling
Refining
Implementation writing
Result & Discussion
Result Gathering
Direct Evaluation
Writing Results
Writing Discussion
Writing Conclusion & Abstract																			Depending on deadlines
Refinement (After Submissions)
Refine Report
Create Presentation

## Date Formatting Strings
LOCAL SPECIFIC DATE STRINGS
Having trouble displaying dates correctly?

Excel's Text() function, which is used extensively to auto-format the spreadsheet, uses "text format strings" to translate
a date into other representations. However, these text format strings are locale-dependent. For example, in the USA
the function Text(A1,"MMM") will return the three-letter month acronym (e.g. "MAR" for March) for a date value.

To get around this problem without writing macros, I'm storing the format strings here for use in the main worksheet.
When you change these values, the "Blank Sheet" and "Example Sheets" will update.

three day month	mmm	change to your locale string (see your Excel documentation for Text() function and dates)

For example, in Turkish, the appropriate strings are:
three day month	mmm

Thanks to Mehmet CAN, a management consultant based in Turkey, for tracking down this issue and providing the solution.
Additonal references:
http://www.rondebruin.nl/international.htm
http://www.excelbanter.com/showthread.php?t=230221